## Schedule
MARTA VENTURES — DETAILED SCHEDULE 2026 (v4.1)
Week | Date | BU | Milestone | Action Items | Budget | Gate | Status
W1 | Jan 1-5 | ALL | Autónomo Registration | Hacienda + RETA (no padrón needed) | €0 | G1
W2 | Jan 6-12 | B | Digital Presence | Website + Instagram live | €150 | B1
W3 | Jan 13-19 | B | Print Production | Order initial prints (20 pcs) | €300 | B1
W4 | Jan 20-26 | A | Trip Planning | Book Mexico flights + hotels | €0
W5 | Jan 27-31 | ALL | Housing + Padrón | Sign contract, empadronamiento | €0
W6 | Feb 1-7 | ALL | Healthcare + Gestor | TSI card, contract gestor | €80
W7 | Feb 8-14 | ALL | Travel to Mexico | Depart Barcelona Feb 14 | €0
W8 | Feb 15-21 | A | OAXACA SOURCING | Alebrijes, textiles, pottery | €1,100 | A2
W9 | Feb 22-28 | A | PUEBLA + CDMX | Talavera, books, return | €1,100 | A2
W10 | Mar 1-3 | A | Inventory Processing | Photo, price, tag all items | €0
W10 | Mar 4-8 | ALL | ARCO Madrid | Gallery networking | €350
W11 | Mar 9-14 | A/B | Market Prep | Display setup, permits | €160
W12 | Mar 15 | A/B | FIRST MARKET | Sant Antoni launch | €150 | A3/B2/G2
W13 | Mar 16-22 | A/B | Second Market | Try Els Encants | €100
W14 | Mar 23-31 | ALL | Q1 Review | Financial review, adjust | €0 | G2
W15-17 | Apr 1-21 | A/B | April Markets | Regular schedule | €300 | B3
W18-21 | Apr 22-May 31 | A/B | Build Momentum | Gallery outreach | €400
W22-26 | Jun 1-30 | A/B | PEAK SEASON | Maximum presence | €400 | G4/A4/B4

## Sim_Commercio
PLAN A: COMMERCIO — Revenue Simulator
Enter your actual inventory items and costs below (blue cells = input)
Item | Category | Cost (€) | Sell Price (€) | Qty | Total Cost | Total Revenue | Margin %
Alebrije - Jaguar | Alebrijes | 25 | 80 | 5 | 125 | 400 | 0.6875
Alebrije - Dragon | Alebrijes | 30 | 95 | 3 | 90 | 285 | 0.68421
Talavera Plate Large | Ceramics | 35 | 120 | 4 | 140 | 480 | 0.70833
Talavera Vase | Ceramics | 40 | 130 | 3 | 120 | 390 | 0.69231
Rebozo Traditional | Textiles | 45 | 150 | 4 | 180 | 600 | 0.7
Embroidered Blouse | Textiles | 30 | 100 | 5 | 150 | 500 | 0.7
Art Book - Frida | Books | 15 | 45 | 6 | 90 | 270 | 0.66667
Art Book - Oaxaca | Books | 18 | 50 | 4 | 72 | 200 | 0.64
SUMMARY
Total Items | 8
Total Quantity | 34
Total Cost | 967
Total Revenue (if all sold) | 3125
Average Margin | 0.68488
Gross Profit (if all sold) | 0
MONTHLY PROJECTION
Sell-through rate/month (%): | 0.15
Stall fees/month: | 150
Est. Monthly Revenue: | 0
Est. Monthly Gross Profit: | -150

## Sim_Artistico
PLAN B: ARTISTICO — Revenue Simulator
Enter your prints and services below
Print Name | Size | Print Cost (€) | Sell Price (€) | Qty Available | Total Cost | Potential Revenue
Barcelona Gothic | A3 | 15 | 120 | 3 | 45 | 360
Oaxaca Colors | A3 | 15 | 120 | 3 | 45 | 360
Mexico City Night | A2 | 25 | 200 | 2 | 50 | 400
Portrait Series #1 | A2 | 25 | 250 | 2 | 50 | 500
Limited Edition #1 | Large | 40 | 400 | 1 | 40 | 400
SERVICES (Optional)
Service | Price (€) | Est. Jobs/Month | Monthly Revenue
Family Portrait Session | 250 | 1 | 250
Event Photography | 300 | 0.5 | 150
Corporate Headshots | 200 | 1 | 200
MONTHLY PROJECTION
Print sales/month (%): | 0.1
Print Revenue/month: | 202
Service Revenue/month: | 600
Total Est. Revenue/month: | 802

## Sim_Professionale
PLAN C: PROFESSIONALE — Revenue Simulator (Optional)
Use this to project film lab revenue IF you activate this business line
Service | Price (€) | Cost/Unit (€) | Est. Rolls/Month | Monthly Revenue | Monthly Cost | Gross Profit
B&W Develop + Scan | 15 | 6.75 | 20 | 300 | 135 | 165
C-41 Develop + Scan | 18 | 9 | 15 | 270 | 135 | 135
E-6 Develop + Scan | 22 | 12 | 5 | 110 | 60 | 50
Rush Service (+50%) | 0 | 0 | 0 | 0 | 0 | 0
WORKSHOPS
Workshop | Price/Person | Attendees | Sessions/Month | Monthly Revenue
Intro to Film | 60 | 4 | 2 | 480
Photo Walk | 45 | 6 | 4 | 1080
Darkroom Basics | 80 | 3 | 1 | 240
MONTHLY SUMMARY
Lab Revenue: | 680
Lab Costs: | 330
Workshop Revenue: | 1800
Total Revenue: | 2480
Total Gross Profit: | 2150

## Transaction_Book
MARTA VENTURES — TRANSACTION BOOK (v4.1)
Record ALL income and expenses here. This is your financial truth.
Date | BU | Type | Category | Description | Income (€) | Expense (€) | Balance | Notes
2026-01-01 | ALL | OPENING | Capital | Initial Capital | 10000 | 0 | 10000 | Starting balance
2026-01-03 | ALL | EXPENSE | Setup | Website domain + hosting |  | 120 | 9880
2026-01-05 | ALL | EXPENSE | Setup | Business cards |  | 30 | 9850
2026-01-18 | B | EXPENSE | Inventory | Print batch #1 (20 prints) |  | 300 | 9550
2026-02-01 | ALL | EXPENSE | Operating | Social Security (Feb) |  | 80 | 9470
2026-02-01 | ALL | EXPENSE | Operating | Gestor (Feb) |  | 50 | 9420
2026-02-14 | A | EXPENSE | Travel | Mexico flights |  | 900 | 8520
2026-02-15 | A | EXPENSE | Travel | Mexico hotels |  | 450 | 8070
2026-02-28 | A | EXPENSE | Inventory | Mexico sourcing - Oaxaca |  | 1200 | 6870
2026-02-28 | A | EXPENSE | Inventory | Mexico sourcing - Puebla |  | 500 | 6370
2026-02-28 | A | EXPENSE | Inventory | Mexico sourcing - books |  | 200 | 6170
2026-03-01 | ALL | EXPENSE | Operating | Social Security (Mar) |  | 80 | 6090
2026-03-01 | ALL | EXPENSE | Operating | Gestor (Mar) |  | 50 | 6040
2026-03-06 | ALL | EXPENSE | Marketing | ARCO Madrid trip |  | 350 | 5690
2026-03-12 | A | EXPENSE | Operating | Display equipment |  | 130 | 5560
2026-03-15 | A | EXPENSE | Operating | Sant Antoni stall fee |  | 150 | 5410
2026-03-15 | A | INCOME | Sales | Market - alebrije x2 | 160 |  | 5570
2026-03-15 | B | INCOME | Sales | Market - print A3 | 120 |  | 5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690
5690

## Dashboard
MARTA VENTURES — FINANCIAL DASHBOARD (v4.1)
SUMMARY BY BUSINESS UNIT
Business Unit | Total Income | Total Expenses | Net | Budget | Remaining
A - Commercio | 160 | 3530 | -3370 | 5500 | 1970
B - Artistico | 120 | 300 | -180 | 1000 | 700
C - Professionale | 0 | 0 | 0 | 0 | 0
ALL - Shared | 10000 | 760 | 9240 | 3500 | 2740
TOTAL | 10280 | 4590 | 5690 | 10000 | 5410
KEY METRICS
Current Balance | 5690
Global Reserve Target | 3000
Reserve Status | OK
Total Income YTD | 10280
Total Expenses YTD | 4590
Net Profit/Loss | 5690
GATE STATUS (Update Manually)
Gate | Target Date | Status | Notes
G1: Launch | Jan 5
G2: First Revenue | Mar 31
A2: Mexico Trip | Feb 28
B1: Portfolio | Jan 12
A3/B2: First Market | Mar 15

## Instructions
HOW TO USE THIS WORKBOOK
BLUE CELLS = INPUT (you fill these in)
WHITE CELLS = FORMULAS (don't edit)
GREEN CELLS = KEY TOTALS
═══════════════════════════════════════════════════════════
SCHEDULE TAB:
• Track progress against the plan
• Update Status column as you complete items
• Use dropdowns: NOT STARTED, IN PROGRESS, DONE, BLOCKED
SIMULATOR TABS (Sim_Commercio, Sim_Artistico, Sim_Professionale):
• Enter your ACTUAL items with real costs and prices
• Simulator calculates margins and projections
• Use this BEFORE buying to validate margins
• Update quantities as you sell items
TRANSACTION BOOK TAB:
• Record EVERY transaction (income and expense)
• Use dropdowns for BU (A, B, C, ALL) and Type (INCOME, EXPENSE)
• Balance updates automatically
• This is your single source of financial truth
DASHBOARD TAB:
• Automatic summary from Transaction Book
• Shows income/expense by business unit
• Update Gate Status manually
• Check Reserve Status regularly
═══════════════════════════════════════════════════════════
WEEKLY ROUTINE:
1. Record all transactions in Transaction Book
2. Check Dashboard for balance and gate status
3. Update Schedule status
MONTHLY ROUTINE:
1. Review Dashboard totals vs budget
2. Update simulators with actual inventory
3. Check gates due this month
QUARTERLY ROUTINE:
1. Full gate review
2. Compare actual vs projected
3. Adjust simulators for next quarter